04/07/17 – Class Meeting Notes

Francesco transcription done

Still waiting on the rest
Taylor has man on street transcriptions
Woodson shoot – Done – Bijan

Logging – since we can only log on one – attached to hard drive
we will move it around the lab computers

Russell Gant went great
livley and informative
got B-Roll
sound bites collected about the orchestra
named Florida Orchestra

Talks about how audience has not declined
realationship of classical music to pop culture
Emotional connection
timelessness
how it helps people relate to one another
different ways orchestra is capturing the

Build a Facebook page
Next week we will for this

There are a great deal of sound bites collected that talk of classical music
even when the interview was a little dark

Interveiws going well this past week
Man on the Street – also went well

93.3 – dodging the interview
Katie Summers interview not working
Cox Media Group? -

JamiKay looking at interviews and looking to get additional B-Roll
There are recitals that can provide B-Roll

By WEDNESDAY – NO MORE SHOOTING

BULLSTOCK?
Not really going to help
do we need it?

Subject – Power of Classical Music

Michael Francis
spoke of future of conducting

Francesco
he talked about USF conducting
how it's difficult to be involved in art community
his goal is to show classical music is not dead

DJ Christian
Classical music is not dead
compares himself to conductor
complexity of classical music
the community outreach of his music

Orchestra musicians
Mosloff, Smith and Wang
what they like the orchestra
their path into the orchestra

Cello Player USF
he talked about how his life is dedicated to his instrument
he has a composing degree

Highschool student
Sam – hustles to get into music

Woodson interviews
Lowel - Cello player
artist who did paintings for the museums

We need to find commonality
put together bites and sections
“WHY DO WE CARE” - focus on that
Find what's important
we are pretty much done shooting

If we stick with Emotion and pop culture
we will have a story

SEGMENT PRODUCERS
Francesco – JamiKay
on time line, Transcription done
Russell – Jeania

Lack of Conflict?
We cannot assume the conflict
this seems to be an issue that is holding us back
Conclusion – this can help us wrap up the subject

Make sure we are keeping the audience engaged
we need to keep their attention so we cannot have interviews rambling