Notes
More footage needed.
Modern music footage (Bullstock April 7th, Potential 93.3 flz interview, Forrest B-roll homecoming footage, Kevin DJ at Ritz Friday the 7th)
SOUND BITES ARE PRIORITY!!!!
BULLSTOCK
- JamiKay, Demi, Queena, Lauren
- 1 School camera and lov mic needed. (Queena getting it)
MAN ON THE STREET
- Forrest heading up
- Thursday noon in front of Cooper hall
- Eric, Christian, Rosalyne, Demi, Spencer and Forrest
WUSF RUSSEL GANT INTERVIEW
- Headed up by Jeania
- Monday April 3rd @ 8:30 a.m. to noon
INTERVIEW WITH D
- Headed up by Kari
- Will probably take place on Saturday or Sunday (potentially the 14th and 15th)
- Need people to take part; contact Kari
DAY IN THE LIFE WITH FRANK
- JamiKay heading it up
- Need day in the life footage and ECU’s of him playing
MORE INTERVIEWS WITH STUDENT AND TFO
- Headed up by Charlie
- Interview Kelly
DEADLINES
- Final Class date is the 21st
- Doc done before exam week end (April 28th)
TO DO
- Segment producers start editing segments when done
- Lower thirds design needs to be set (JamiKay)
FYI
Contact Ryan Watson for any questions not Kristin (email: rawatso2@usf.edu)